## Hospital
Active | Task Name | Task Nesting | Actual Dates Enabled | Actual Start | Actual End | Planned Dates Enabled | Duration | Planned Start | Planned End | Task Type | Attached | Script | Data Source | Synchronization ID | Display ID | Animation | Animation Behaviour | Provided Progress % | Comments | Material Cost | Labor Cost | Equipment Cost | Subcontractor Cost | User 1 | User 2 | User 3 | User 4 | User 5 | User 6 | User 7 | User 8 | User 9 | User 10
1 | Site | 0 |  |  |  | 1 |  | 2013-01-02 | [5 empty] | 100 | 100 |  | Scale | 0% | 0
1 | Existing site/ground | 1 | [11 empty] | 100-1 | 100-1 |  | Scale | 0% | 0
1 | Topography | 2 | 1 |  |  | 1 | 360 | 2013-01-02 | 2013-12-28 | Temporary | Explicit Selection |  |  | 100-1-1 | 100-1-1 |  | Scale | 0% | 0
| Excavate Site | 2 | 1 |  |  | 1 | 10 | 2013-01-02 | 2013-01-12 | Construct |  |  |  | 100-1-2 | 100-1-2 |  | Scale | 0% |  | 224997 | 45000 | 400000
1 | Mobilize & Secure Site | 1 | [11 empty] | 100-2 | 100-2 |  | Scale | 0% | 0
1 | Fence_Chainlink_Reed | 2 | 1 | 2012-12-28 | 2014-03-08 09:00 | 1 | 430 | 2013-01-02 | 2014-03-08 | Temporary | Sets->Site->Fence_Chainlink_Reed |  |  | 100-2-1 | 100-2-1 |  | Scale | 0% | 0 | 120000 | 50000 | 0 | 0
1 | Construction Trailer | 2 | 1 | 2013-01-01 01:55 | 2014-04-02 06:00 | 1 | 450 | 2013-01-07 | 2014-04-02 | Temporary | Sets->Site->Construction Trailer |  |  | 100-2-2 | 100-2-2 |  | Scale | 0% | 0 |  | 0 | 455000 | 0
1 | Storage Container | 2 | 1 | 2012-12-31 04:48 | 2014-03-13 01:55 | 1 | 430 | 2013-01-07 | 2014-03-13 | Temporary | Sets->Site->Storage Container |  |  | 100-2-3 | 100-2-3 |  | Scale | 0% | 0 |  | 0 | 525000 | 0
1 | Tool Trailer | 2 | 1 | 2013-01-02 | 2014-07-22 01:55 | 1 | 561 | 2013-01-07 | 2014-07-22 | Temporary | Sets->Site->Tool Trailer |  |  | 100-2-4 | 100-2-4 |  | Scale | 0% | 0 |  | 0 | 400000 | 0
1 | Porta-John | 2 | 1 | 2013-01-04 08:24 | 2013-01-04 09:22 | 1 | 561 | 2013-01-07 | 2014-07-22 | Temporary | Sets->Site->Porta-John |  |  | 100-2-5 | 100-2-5 |  | Scale | 0% | 0 |  | 0 | 25000 | 0
1 | Waste Container | 2 | 1 | 2013-01-04 07:12 | 2014-07-22 00:58 | 1 | 561 | 2013-01-07 | 2014-07-22 | Temporary | Sets->Site->Waste_Container |  |  | 100-2-6 | 100-2-6 |  | Scale | 0% | 0 |  | 0 | 560000 | 0
1 | Pickup Truck | 2 | 1 | 2012-12-28 |  | 1 | 430 | 2013-01-04 | 2014-03-10 | Equipment | Sets->Site->Pick-Up_Truck |  |  | 100-2-7 | 100-2-7 |  | Scale | 0% | 0 | 300000 | 0 | 0 | 0
1 | Lay-Down Pad | 2 | 1 | 2013-01-08 |  | 1 | 200 | 2013-01-12 | 2013-07-31 | Temporary | Sets->Site->Lay-Down Pad |  |  | 100-2-8 | 100-2-8 |  | Scale | 0% | 0 | 200000 | 0 | 0 | 0
1 | Construction Crane | 2 | 1 | 2013-01-16 12:00 |  | 1 | 150 | 2013-01-16 12:00 | 2013-06-15 12:00 | Equipment | Sets->Site->Construction_Crane |  |  | 100-2-9 | 100-2-9 |  | Scale | 0% | 0 |  | 0 | 40000 | 0
1 | Concrete Truck | 2 | 1 | 2013-02-09 12:00 |  | 1 | 68 | 2013-02-07 12:00 | 2013-04-16 12:00 | Equipment | Sets->Site->Concrete_Truck |  |  | 100-2-10 | 100-2-10 |  | Scale | 0% | 0 | 550000 | 120000 | 135000
1 | Concrete Boom Pump Truck | 2 | 1 | 2013-02-09 12:00 |  | 1 | 68 | 2013-02-07 12:00 | 2013-04-16 12:00 | Equipment | Sets->Site->Concrete Boom Pump Truck |  |  | 100-2-11 | 100-2-11 |  | Scale | 0% | 0 | 150000 | 50000 | 150000 | 0
1 | Tower Crane | 1 | [11 empty] | 100-3 | 100-3
1 | TowerCrane-Assemble | 2 | 1 |  |  | 1 | 5 | 2013-04-05 12:00 | 2013-04-10 12:00 | Equipment-Setup | Sets->Tower_Crane |  |  | 100-3-1 | 100-3-1 |  | Scale | 0% | 0 | 915800 | 165500
1 | TowerCrane-Use | 2 | 1 |  |  | 1 | 177 | 2013-04-10 12:00 | 2013-10-04 12:00 | Equipment | Sets->Tower_Crane |  |  | 100-3-2 | 100-3-2 |  | Scale | 0% | 0 |  |  | 885000
1 | TowerCrane-Disassemble | 2 | 1 |  |  | 1 | 3 | 2013-10-04 12:00 | 2013-10-07 12:00 | Demolish | Sets->Tower_Crane |  |  | 100-3-3 | 100-3-3 |  | Scale | 0% | 0 |  | 42000
1 | Structural | 0 |  |  |  | 1 | [7 empty] | 200 | 200 |  | Scale | 0% | 0
1 | Structural - Foundation | 1 |  |  |  | 1 | [7 empty] | 200-1 | 200-1 |  | Scale | 0% | 0
1 | Drill_rig | 2 |  |  |  |  | 11 | 2013-01-12 | 2013-01-23 | Equipment | Explicit Selection |  |  | 200-1-1 | 200-1-1 | Pile Hole Drilling | Scale | 0% | 0 | 155000 | 75000 | 158872
1 | Struct-Fndn-Pile_Pipe | 2 | 1 | 2013-01-17 12:00 | 2013-02-05 20:24 | 1 | 20 | 2013-01-17 12:00 | 2013-02-06 12:00 | Construct | Sets->Structural->Foundation->Struct-Fndn-Pile_Pipe |  |  | 200-1-2 | 200-1-2 |  | Scale | 0% | 0 | 165000 | 150000 | 152868 | 0
1 | Struct-Fndn-Pile_Cap | 2 | 1 | 2013-02-09 12:00 | 2013-03-01 16:48 | 1 | 20 | 2013-02-07 12:00 | 2013-02-27 12:00 | Construct | Sets->Structural->Foundation->Struct-Fndn-Pile_Cap |  |  | 200-1-3 | 200-1-3 |  | Scale | 0% | 0 | 81495 | 126000 | 0 | 0
1 | Struct-Fndn-Footings | 2 | 1 | 2013-03-03 12:00 | 2013-03-15 19:12 | 1 | 10 | 2013-02-28 12:00 | 2013-03-10 12:00 | Construct | Sets->Structural->Foundation->Struct-Fndn-Footings |  |  | 200-1-4 | 200-1-4 |  | Scale | 0% | 0 | 147153 | 216600 | 0 | 0
1 | Underslap MEP/Utilities | 2 | 1 |  |  |  | 20 | 2013-03-10 12:00 | 2013-03-30 12:00 | Construct |  |  |  | 200-1-5 | 200-1-5 |  | Scale | 0% | 0 | 65477 | 12550 | 0 | 0
1 | Struct-Fndn-Concrete Slabs_Walls_Columns | 2 | 1 | 2013-03-19 12:00 | 2013-04-10 | 1 | 25 | 2013-03-11 12:00 | 2013-04-05 12:00 | Construct | Sets->Structural->Foundation->Struct-Fndn-Concrete Slabs, Walls, Columns |  |  | 200-1-6 | 200-1-6 |  | Scale | 0% | 0 | 113862 | 75000 | 0 | 0
1 | Backfill Foundations | 2 | 1 | 2013-04-10 |  |  | 3 | 2013-04-05 12:00 | 2013-04-08 12:00 | Construct |  |  |  | 200-1-7 | 200-1-7 | Bulldozer | Scale | 0% | 0 | 945000 | 50000 | 25490 | 0
1 | Struct-Floor-L1 | 2 | 1 | 2013-04-12 | 2013-04-20 | 1 | 8 | 2013-04-08 12:00 | 2013-04-16 12:00 | Construct | Sets->Structural->Floors->Struct-Floor-L1 |  |  | 200-1-8 | 200-1-8 |  | Scale | 0% | 0 | 1508436 | 76374 | 0 | 0
1 | Structural - Steel | 1 |  |  |  | 1 | [7 empty] | 200-2 | 200-2 |  | Scale | 0% | 0
1 | folding_crane | 2 | 1 |  |  | 1 | 45 | 2013-04-21 12:00 | 2013-06-05 12:00 | Equipment | Explicit Selection |  |  | 200-2-1 | 200-2-1 |  | Scale | 0% | 0 |  |  | 80000
1 | Struct-Col-BaseL1 | 2 | 1 | 2013-04-23 12:00 |  | 1 | 4 | 2013-04-23 12:00 | 2013-04-27 12:00 | Construct | Sets->Structural->Columns->Struct-Col-BaseL1 |  |  | 200-2-2 | 200-2-2 |  | Scale | 0% | 0 | 1255000 | 0 | 0 | 22540
1 | Struct-Framing-L2 | 2 | 1 |  |  | 1 | 5 | 2013-04-28 12:00 | 2013-05-03 12:00 | Construct | Sets->Structural->Framing->Struct-Framing-L2 |  |  | 200-2-3 | 200-2-3 |  | Scale | 0% | 0 | 1687000 | 0 | 0 | 25454
1 | Struct-Framing-L3 | 2 | 1 |  |  | 1 | 6 | 2013-05-04 12:00 | 2013-05-10 12:00 | Construct | Sets->Structural->Framing->Struct-Framing-L3 |  |  | 200-2-4 | 200-2-4 |  | Scale | 0% | 0 | 1365500 | 0 | 0 | 25458
1 | Struct-Col-BaseL3 | 2 | 1 |  |  | 1 | 4 | 2013-05-05 12:00 | 2013-05-09 12:00 | Construct | Sets->Structural->Columns->Struct-Col-BaseL3 |  |  | 200-2-5 | 200-2-5 |  | Scale | 0% | 0 | 1178550 | 0 | 0 | 215578
1 | Struct-Framing-L4 | 2 | 1 |  |  | 1 | 5 | 2013-05-10 12:00 | 2013-05-15 12:00 | Construct | Sets->Structural->Framing->Struct-Framing-L4 |  |  | 200-2-6 | 200-2-6 |  | Scale | 0% | 0 | 1321425 | 0 | 0 | 44548
1 | Struct-Col-BaseL4 | 2 | 1 |  |  | 1 | 1 | 2013-05-11 12:00 | 2013-05-12 12:00 | Construct | Sets->Structural->Columns->Struct-Col-BaseL4 |  |  | 200-2-7 | 200-2-7 |  | Scale | 0% | 0 | 1174200 | 0 | 0 | 44000
1 | Struct-Framing-L5 | 2 | 1 |  |  | 1 | 5 | 2013-05-13 12:00 | 2013-05-18 12:00 | Construct | Sets->Structural->Framing->Struct-Framing-L5 |  |  | 200-2-8 | 200-2-8 |  | Scale | 0% | 0 | 1232541 | 0 | 0 | 25487
1 | Struct-Col-BaseL5 | 2 | 1 |  |  | 1 | 4 | 2013-05-14 12:00 | 2013-05-18 12:00 | Construct | Sets->Structural->Columns->Struct-Col-BaseL5 |  |  | 200-2-9 | 200-2-9 |  | Scale | 0% | 0 | 1325444 | 0 | 0 | 114451
1 | Struct-Framing-L6 | 2 | 1 |  |  | 1 | 3 | 2013-05-19 12:00 | 2013-05-22 12:00 | Construct | Sets->Structural->Framing->Struct-Framing-L6 |  |  | 200-2-10 | 200-2-10 |  | Scale | 0% | 0 | 1325444 | 0 | 0 | 124514
1 | Struct-Framing-L7 | 2 | 1 |  |  | 1 | 3 | 2013-05-23 12:00 | 2013-05-26 12:00 | Construct | Sets->Structural->Framing->Struct-Framing-L7 |  |  | 200-2-11 | 200-2-11 |  | Scale | 0% | 0 | 1325444 | 0 | 0 | 124425
1 | Structural - Floor - Metal Decking and Concrete | 1 |  |  |  | 1 | [7 empty] | 200-3 | 200-3 |  | Scale | 0% | 0
1 | Struct-Floor-MetalDeck-L2 | 2 | 1 |  |  | 1 | 4 | 2013-05-10 12:00 | 2013-05-14 12:00 | Construct | Sets->Structural->Floors->Metal Decking (By Level)->Struct-Floor-MetalDeck-L2 |  |  | 200-3-1 | 200-3-1 |  | Scale | 0% | 0 | 1965000 | 0 | 0 | 252551
1 | Struct-Floor-MetalDeck-L3 | 2 | 1 |  |  | 1 | 5 | 2013-05-14 12:00 | 2013-05-19 12:00 | Construct | Sets->Structural->Floors->Metal Decking (By Level)->Struct-Floor-MetalDeck-L3 |  |  | 200-3-2 | 200-3-2 |  | Scale | 0% | 0 | 1765000 | 0 | 0 | 152551
1 | Struct-Floor-MetalDeck-L4 | 2 | 1 |  |  | 1 | 4 | 2013-05-19 12:00 | 2013-05-23 12:00 | Construct | Sets->Structural->Floors->Metal Decking (By Level)->Struct-Floor-MetalDeck-L4 |  |  | 200-3-3 | 200-3-3 |  | Scale | 0% | 0 | 1665000 | 0 | 0 | 152551
1 | Struct-Floor-MetalDeck-L5 | 2 | 1 |  |  | 1 | 5 | 2013-05-23 12:00 | 2013-05-28 12:00 | Construct | Sets->Structural->Floors->Metal Decking (By Level)->Struct-Floor-MetalDeck-L5 |  |  | 200-3-4 | 200-3-4 |  | Scale | 0% | 0 | 1765000 | 0 | 0 | 152551
1 | Struct-Floor-MetalDeck-L6 | 2 | 1 |  |  | 1 | 4 | 2013-05-28 12:00 | 2013-06-01 12:00 | Construct | Sets->Structural->Floors->Metal Decking (By Level)->Struct-Floor-MetalDeck-L6 |  |  | 200-3-5 | 200-3-5 |  | Scale | 0% | 0 | 1765000 | 0 | 0 | 152551
1 | Struct-Floor-MetalDeck-L7 | 2 | 1 |  |  | 1 | 4 | 2013-06-01 12:00 | 2013-06-05 12:00 | Construct | Sets->Structural->Floors->Metal Decking (By Level)->Struct-Floor-MetalDeck-L7 |  |  | 200-3-6 | 200-3-6 |  | Scale | 0% | 0 | 1765000 | 0 | 0 | 152551
1 | Struct-Floor-Concrete-L2 | 2 | 1 |  |  | 1 | 5 | 2013-05-20 12:00 | 2013-05-25 12:00 | Construct | Sets->Structural->Floors->Concrete (By Level)->Struct-Floor-Concrete-L2 |  |  | 200-3-7 | 200-3-7 |  | Scale | 0% | 0 | 730000 | 0 | 0 | 132500
1 | Struct-Floor-Concrete-L3 | 2 | 1 |  |  | 1 | 5 | 2013-05-25 12:00 | 2013-05-30 12:00 | Construct | Sets->Structural->Floors->Concrete (By Level)->Struct-Floor-Concrete-L3 |  |  | 200-3-8 | 200-3-8 |  | Scale | 0% | 0 | 730000 | 0 | 0 | 132500
1 | Struct-Floor-Concrete-L4 | 2 | 1 |  |  | 1 | 5 | 2013-05-30 12:00 | 2013-06-04 12:00 | Construct | Sets->Structural->Floors->Concrete (By Level)->Struct-Floor-Concrete-L4 |  |  | 200-3-9 | 200-3-9 |  | Scale | 0% | 0 | 730000 | 0 | 0 | 132500
1 | Struct-Floor-Concrete-L5 | 2 | 1 |  |  | 1 | 5 | 2013-06-04 12:00 | 2013-06-09 12:00 | Construct | Sets->Structural->Floors->Concrete (By Level)->Struct-Floor-Concrete-L5 |  |  | 200-3-10 | 200-3-10 |  | Scale | 0% | 0 | 730000 | 0 | 0 | 132500
1 | Struct-Floor-Concrete-L6 | 2 | 1 |  |  | 1 | 5 | 2013-06-09 12:00 | 2013-06-14 12:00 | Construct | Sets->Structural->Floors->Concrete (By Level)->Struct-Floor-Concrete-L6 |  |  | 200-3-11 | 200-3-11 |  | Scale | 0% | 0 | 730000 | 0 | 0 | 132500
1 | Struct-Floor-Concrete-L7 | 2 | 1 |  |  | 1 | 5 | 2013-06-14 12:00 | 2013-06-19 12:00 | Construct | Sets->Structural->Floors->Concrete (By Level)->Struct-Floor-Concrete-L7 |  |  | 200-3-12 | 200-3-12 |  | Scale | 0% | 0 | 530000 | 0 | 0 | 112500
1 | Dock Stairs | 1 |  |  |  | 1 | [7 empty] | 200-4 | 200-4 |  | Scale | 0% | 0
1 | Struct-Dock_StairSteps | 2 | 1 |  |  | 1 | 1 | 2013-05-21 12:00 | 2013-05-22 12:00 | Construct | Sets->Structural->Dock Stairs->Struct-Dock_StairSteps |  |  | 200-4-1 | 200-4-1 |  | Scale | 0% | 0 | 1500000 | 0 | 0 | 150000
1 | Struct-Dock_Railing | 2 | 1 |  |  | 1 | 1 | 2013-05-22 12:00 | 2013-05-23 12:00 | Construct | Sets->Structural->Dock Stairs->Struct-Dock_Railing |  |  | 200-4-2 | 200-4-2 |  | Scale | 0% | 0 | 750000 | 0 | 0 | 100000
1 | Architectural | 0 |  |  |  | 1 | [7 empty] | 300 | 300 |  | Scale | 0% | 0
1 | Exterior | 1 |  |  |  | 1 | [7 empty] | 300-1 | 300-1 |  | Scale | 0% | 0
1 | Walls | 2 |  |  |  | 1 | [7 empty] | 300-1-1 | 300-1-1 |  | Scale | 0% | 0
1 | Scaffolding | 3 | 1 |  |  | 1 | 30 | 2013-06-03 12:00 | 2013-07-03 12:00 | Temporary | Sets->Site->Scaffolding |  |  | 3101-1 | 3101-1 |  | Scale | 100% | 0 |  |  | 12400
1 | Arch-Ext-Wall-L1 | 3 | 1 |  |  | 1 | 8 | 2013-06-07 12:00 | 2013-06-15 12:00 | Construct | Sets->Architectural->Exterior->Walls->Arch-Ext-Wall-L1 |  |  | 3101-2 | 3101-2 |  | Scale | 0% | 0 | 1550000 | 128000 | 0 | 20800
1 | Arch-Ext-Wall-L2 | 3 | 1 |  |  | 1 | 10 | 2013-06-14 12:00 | 2013-06-24 12:00 | Construct | Sets->Architectural->Exterior->Walls->Arch-Ext-Wall-L2 |  |  | 3101-3 | 3101-3 |  | Scale | 0% | 0 | 1530000 | 128000 | 0 | 26000
1 | Arch-Ext-Wall-L3 | 3 | 1 |  |  | 1 | 8 | 2013-06-23 12:00 | 2013-07-01 12:00 | Construct | Sets->Architectural->Exterior->Walls->Arch-Ext-Wall-L3 |  |  | 3101-4 | 3101-4 |  | Scale | 0% | 0 | 1165000 | 128000 | 0 | 20800
1 | Arch-Ext-Wall-L4 | 3 | 1 |  |  | 1 | 12 | 2013-06-30 12:00 | 2013-07-12 12:00 | Construct | Sets->Architectural->Exterior->Walls->Arch-Ext-Wall-L4 |  |  | 3101-5 | 3101-5 |  | Scale | 0% | 0 | 1165000 | 128000 | 0 | 31200
1 | Arch-Ext-Wall-L5 | 3 | 1 |  |  | 1 | 12 | 2013-07-11 12:00 | 2013-07-23 12:00 | Construct | Sets->Architectural->Exterior->Walls->Arch-Ext-Wall-L5 |  |  | 3101-6 | 3101-6 |  | Scale | 0% | 0 | 1163000 | 128000 | 0 | 31200
1 | Arch-Ext-Wall-L6 | 3 | 1 |  |  | 1 | 10 | 2013-07-22 12:00 | 2013-08-01 12:00 | Construct | Sets->Architectural->Exterior->Walls->Arch-Ext-Wall-L6 |  |  | 3101-7 | 3101-7 |  | Scale | 0% | 0 | 1185000 | 128000 | 0 | 26000
1 | Arch-Ext-Wall-L7 | 3 | 1 |  |  | 1 | 14 | 2013-07-31 12:00 | 2013-08-14 12:00 | Construct | Sets->Architectural->Exterior->Walls->Arch-Ext-Wall-L7 |  |  | 3101-8 | 3101-8 |  | Scale | 0% | 0 | 1145000 | 128000 | 0 | 36400
1 | Arch-Ext-BeamSoffit+Enclosure | 2 | 1 |  |  | 1 | 3 | 2013-08-13 12:00 | 2013-08-16 12:00 | Construct | Sets->Architectural->Exterior->Arch-Ext-BeamSoffit+Enclosure |  |  | 3101-9 | 3101-9 |  | Scale | 0% | 0 | 1150000 | 128000 | 0 | 7800
1 | Curtain Walls and Windows | 2 |  |  |  | 1 | [7 empty] | 300-1-2 | 300-1-2 |  | Scale | 0% | 0
1 | Arch-Ext-CurtWall_Windows-L1 | 3 | 1 |  |  | 1 | 8 | 2013-06-12 12:00 | 2013-06-20 12:00 | Construct | Sets->Architectural->Exterior->Curtain Walls and Windows->Arch-Ext-CurtWall_Windows-L1 |  |  | 3102-1 | 3102-1 |  | Scale | 0% | 0 | 1775000 | 0 | 0 | 775000
1 | Arch-Ext-CurtWall_Windows-L2 | 3 | 1 |  |  | 1 | 10 | 2013-06-21 12:00 | 2013-07-01 12:00 | Construct | Sets->Architectural->Exterior->Curtain Walls and Windows->Arch-Ext-CurtWall_Windows-L2 |  |  | 3102-2 | 3102-2 |  | Scale | 0% | 0 | 1750000 | 0 | 0 | 775000
1 | Arch-Ext-CurtWall-L3 | 3 | 1 |  |  | 1 | 10 | 2013-07-02 12:00 | 2013-07-12 12:00 | Construct | Sets->Architectural->Exterior->Curtain Walls and Windows->Arch-Ext-CurtWall-L3 |  |  | 3102-4 | 3102-4 |  | Scale | 0% | 0 | 950000 | 0 | 0 | 195000
1 | Arch-Ext-CurtWall-L4 | 3 | 1 |  |  | 1 | 10 | 2013-07-13 12:00 | 2013-07-23 12:00 | Construct | Sets->Architectural->Exterior->Curtain Walls and Windows->Arch-Ext-CurtWall-L4 |  |  | 3102-5 | 3102-5 |  | Scale | 0% | 0 | 750000 | 0 | 0 | 175000
1 | Arch-Ext-CurtWall-L5 | 3 | 1 |  |  | 1 | 10 | 2013-07-24 12:00 | 2013-08-03 12:00 | Construct | Sets->Architectural->Exterior->Curtain Walls and Windows->Arch-Ext-CurtWall-L5 |  |  | 3102-6 | 3102-6 |  | Scale | 0% | 0 | 750000 | 0 | 0 | 175000
1 | Arch-Ext-CurtWall-L6 | 3 | 1 |  |  | 1 | 10 | 2013-08-04 12:00 | 2013-08-14 12:00 | Construct | Sets->Architectural->Exterior->Curtain Walls and Windows->Arch-Ext-CurtWall-L6 |  |  | 3102-7 | 3102-7 |  | Scale | 0% | 0 | 750000 | 0 | 0 | 175000
1 | Columns and Sweeps | 2 | 1 |  |  | 1 | [7 empty] | 300-1-3 | 300-1-3 |  | Scale | 0% | 0
1 | Arch-Ext-Col_Sweeps-L1+L2 | 3 | 1 |  |  | 1 | 8 | 2013-07-12 12:00 | 2013-07-20 12:00 | Construct | Sets->Architectural->Exterior->Columns and Sweeps->Arch-Ext-Col_Sweeps-L1+L2 |  |  | 300-1-3-1 | 300-1-3-1 |  | Scale | 0% | 0 | 1250000 | 0 | 0 | 0
1 | Doors | 2 | 1 |  |  | 1 | [7 empty] | 300-1-4 | 300-1-4 |  | Scale | 0% | 0
1 | Arch-Ext-Doors-L1 | 3 | 1 |  |  | 1 | 0.5 | 2013-06-15 12:00 | 2013-06-16 | Construct | Sets->Architectural->Exterior->Doors->Arch-Ext-Doors-L1 |  |  | 300-1-4-1 | 300-1-4-1 |  | Scale | 0% | 0 | 1550000 | 0 | 0 | 300000
1 | Arch-Ext-Doors-L6 | 3 | 1 |  |  | 1 | 0.5 | 2013-08-16 | 2013-08-16 12:00 | Construct | Sets->Architectural->Exterior->Doors->Arch-Ext-Doors-L6 |  |  | 300-1-4-2 | 300-1-4-2 |  | Scale | 0% | 0 | 1225000 | 0 | 0 | 75000
1 | Arch-Ext-Doors-L7 | 3 | 1 |  |  | 1 | 0.5 | 2013-08-16 12:00 | 2013-08-17 | Construct | Sets->Architectural->Exterior->Doors->Arch-Ext-Doors-L7 |  |  | 300-1-4-3 | 300-1-4-3 |  | Scale | 0% | 0 | 1225000 | 0 | 0 | 70000
1 | Roof | 2 | 1 |  |  | 1 | [7 empty] | 300-1-5 | 300-1-5 |  | Scale | 0% | 0
1 | Arch-Ext-Louver-L6+7 | 3 | 1 |  |  | 1 | 2 | 2013-08-13 12:00 | 2013-08-15 12:00 | Construct | Sets->Architectural->Exterior->Arch-Ext-Louver-L6+7 |  |  | 300-1-5-1 | 300-1-5-1 |  | Scale | 0% | 0 | 1250000 | 0 | 0 | 145000
1 | Arch-Ext-Roof-L2 | 3 | 1 |  |  | 1 | 3 | 2013-08-16 12:00 | 2013-08-19 12:00 | Construct | Sets->Architectural->Exterior->Roof->By Level->Arch-Ext-Roof-L2 |  |  | 300-1-5-2 | 300-1-5-2 |  | Scale | 0% | 0 | 450000 | 0 | 0 | 165000
1 | Arch-Ext-Roof-L3 | 3 | 1 |  |  | 1 | 10 | 2013-08-19 12:00 | 2013-08-29 12:00 | Construct | Sets->Architectural->Exterior->Roof->By Level->Arch-Ext-Roof-L3 |  |  | 300-1-5-3 | 300-1-5-3 |  | Scale | 0% | 0 | 682000 | 0 | 0 | 123500
1 | Arch-Ext-Roof-L4 | 3 | 1 |  |  | 1 | 2 | 2013-08-29 12:00 | 2013-08-31 12:00 | Construct | Sets->Architectural->Exterior->Roof->By Level->Arch-Ext-Roof-L4 |  |  | 300-1-5-4 | 300-1-5-4 |  | Scale | 0% | 0 | 425000 | 0 | 0 | 25000
1 | Arch-Ext-Roof-L5 | 3 | 1 |  |  | 1 | 2 | 2013-08-31 12:00 | 2013-09-02 12:00 | Construct | Sets->Architectural->Exterior->Roof->By Level->Arch-Ext-Roof-L5 |  |  | 300-1-5-5 | 300-1-5-5 |  | Scale | 0% | 0 | 422000 | 0 | 0 | 15000
1 | Arch-Ext-Roof-L6 | 3 | 1 |  |  | 1 | 2 | 2013-09-02 12:00 | 2013-09-04 12:00 | Construct | Sets->Architectural->Exterior->Roof->By Level->Arch-Ext-Roof-L6 |  |  | 300-1-5-6 | 300-1-5-6 |  | Scale | 0% | 0 | 880000 | 0 | 0 | 20000
1 | Arch-Ext-Roof-L7 | 3 | 1 |  |  | 1 | 15 | 2013-09-04 12:00 | 2013-09-19 12:00 | Construct | Sets->Architectural->Exterior->Roof->By Level->Arch-Ext-Roof-L7 |  |  | 300-1-5-7 | 300-1-5-7 |  | Scale | 0% | 0 | 1255000 | 0 | 0 | 54851
1 | Courtyard | 2 | 1 |  |  | 1 | [7 empty] | 300-1-6 | 300-1-6 |  | Scale | 0% | 0
1 | Arch-Ext-Roof_Plantings | 3 | 1 |  |  | 1 | 15 | 2013-09-29 12:00 | 2013-10-14 12:00 | Construct | Sets->Architectural->Exterior->Roof->Courtyard->Arch-Ext-Roof_Plantings |  |  | 300-1-6-1 | 300-1-6-1 |  | Scale | 0% | 0 | 525000 | 0 | 0 | 75000
1 | Arch-Ext-Roof_ParkBenches | 3 | 1 |  |  | 1 | 2 | 2013-10-14 12:00 | 2013-10-16 12:00 | Construct | Sets->Architectural->Exterior->Roof->Courtyard->Arch-Ext-Roof_ParkBenches |  |  | 300-1-6-2 | 300-1-6-2 |  | Scale | 0% | 0 | 175000 | 0 | 0 | 25000
1 | Arch-Helipad | 2 | 1 |  |  | 1 | 10 | 2013-09-19 12:00 | 2013-09-29 12:00 | Construct | Sets->Architectural->Exterior->Roof->Arch-Helipad |  |  | 300-1-6-3 | 300-1-6-3 |  | Scale | 0% | 0 | 325000 | 0 | 0 | 54851
1 | Interior | 1 | 1 |  |  | 1 | [7 empty] | 300-2 | 300-2 |  | Scale | 0% | 0
1 | Arch-Int-Elevators | 2 | 1 |  |  | 1 | 80 | 2013-09-04 12:00 | 2013-11-23 12:00 | Construct | Sets->Architectural->Interior->Arch-Int-Elevators |  |  | 300-2-1 | 300-2-1 |  | Scale | 0% | 0 | 15200000 | 0 | 0 | 176000
1 | Arch-Int-WaterFountain | 2 | 1 |  |  | 1 | 8 | 2013-11-23 12:00 | 2013-12-01 12:00 | Construct | Sets->Architectural->Interior->Arch-Int-WaterFountain |  |  | 300-2-2 | 300-2-2 |  | Scale | 0% | 0 | 1500000 | 356000 | 0 | 0
1 | Arch-Int-FixedWindows | 2 | 1 |  |  | 1 | 3 | 2014-05-05 12:00 | 2014-05-08 12:00 | Construct | Sets->Architectural->Interior->Arch-Int-FixedWindows |  |  | 300-2-3 | 300-2-3 |  | Scale | 0% | 0 | 2145000 | 580000 | 0 | 0
1 | Arch-Int-Casework+Counters+InfoDesk | 2 | 1 |  |  | 1 | 10 | 2013-12-01 12:00 | 2013-12-11 12:00 | Construct | Sets->Architectural->Interior->Arch-Int-Casework+Counters+InfoDesk |  |  | 300-2-4 | 300-2-4 |  | Scale | 0% | 0 | 2700000 | 660000 | 0 | 0
1 | Arch-Int-Stairs+Railings | 2 | 1 |  |  | 1 | 45 | 2014-06-11 12:00 | 2014-07-26 12:00 | Construct | Sets->Architectural->Interior->Arch-Int-Stairs+Railings |  |  | 300-2-5 | 300-2-5 |  | Scale | 0% | 0 | 1547888 | 94500 | 0 | 0
1 | Arch-Int-Atrium Railings | 2 | 1 |  |  | 1 | 16 | 2014-07-26 12:00 | 2014-08-11 12:00 | Construct | Sets->Architectural->Interior->Arch-Int-Atrium Railings |  |  | 300-2-6 | 300-2-6 |  | Scale | 0% | 0 | 1526000 | 33600 | 0 | 0
1 | Walls | 2 | 1 |  |  | 1 | [7 empty] | 300-2-7 | 300-2-7 |  | Scale | 0% | 0
1 | Arch-Int-Wall-L1 | 3 | 1 |  |  | 1 | 30 | 2013-12-13 12:00 | 2014-01-12 12:00 | Construct | Sets->Architectural->Interior->Walls->Arch-Int-Wall-L1 |  |  | 300-2-7-1 | 300-2-7-1 |  | Scale | 0% | 0 | 1750000 | 63000 | 0 | 42000
1 | Arch-Int-Wall-L2 | 3 | 1 |  |  | 1 | 30 | 2014-01-12 12:00 | 2014-02-11 12:00 | Construct | Sets->Architectural->Interior->Walls->Arch-Int-Wall-L2 |  |  | 300-2-7-2 | 300-2-7-2 |  | Scale | 0% | 0 | 1250000 | 63000 | 0 | 42000
1 | Arch-Int-Wall-L3 | 3 | 1 |  |  | 1 | 30 | 2014-02-11 12:00 | 2014-03-13 12:00 | Construct | Sets->Architectural->Interior->Walls->Arch-Int-Wall-L3 |  |  | 300-2-7-3 | 300-2-7-3 |  | Scale | 0% | 0 | 1250000 | 63000 | 0 | 42000
1 | Arch-Int-Wall-L4 | 3 | 1 |  |  | 1 | 30 | 2014-03-13 12:00 | 2014-04-12 12:00 | Construct | Sets->Architectural->Interior->Walls->Arch-Int-Wall-L4 |  |  | 300-2-7-4 | 300-2-7-4 |  | Scale | 0% | 0 | 1250000 | 63000 | 0 | 42000
1 | Arch-Int-Wall-L5 | 3 | 1 |  |  | 1 | 30 | 2014-04-12 12:00 | 2014-05-12 12:00 | Construct | Sets->Architectural->Interior->Walls->Arch-Int-Wall-L5 |  |  | 300-2-7-5 | 300-2-7-5 |  | Scale | 0% | 0 | 750000 | 63000 | 0 | 42000
1 | Arch-Int-Wall-L6 | 3 | 1 |  |  | 1 | 30 | 2014-05-12 12:00 | 2014-06-11 12:00 | Construct | Sets->Architectural->Interior->Walls->Arch-Int-Wall-L6 |  |  | 300-2-7-6 | 300-2-7-6 |  | Scale | 0% | 0 | 750000 | 63000 | 0 | 42000
1 | Doors | 2 | 1 |  |  | 1 | [7 empty] | 300-2-8 | 300-2-8 |  | Scale | 0% | 0
1 | Arch-Int-Doors-L1 | 3 | 1 |  |  | 1 | 25 | 2014-02-27 12:00 | 2014-03-24 12:00 | Construct | Sets->Architectural->Interior->Doors->Arch-Int-Doors-L1 |  |  | 300-2-8-1 | 300-2-8-1 |  | Scale | 0% | 0 | 1690000 | 35000 | 0 | 0
1 | Arch-Int-Doors-L2 | 3 | 1 |  |  | 1 | 20 | 2014-03-24 12:00 | 2014-04-13 12:00 | Construct | Sets->Architectural->Interior->Doors->Arch-Int-Doors-L2 |  |  | 300-2-8-2 | 300-2-8-2 |  | Scale | 0% | 0 | 147000 | 28000 | 0 | 0
1 | Arch-Int-Doors-L3 | 3 | 1 |  |  | 1 | 22 | 2014-04-13 12:00 | 2014-05-05 12:00 | Construct | Sets->Architectural->Interior->Doors->Arch-Int-Doors-L3 |  |  | 300-2-8-3 | 300-2-8-3 |  | Scale | 0% | 0 | 208250 | 30800 | 0 | 0
1 | Arch-Int-Doors-L4 | 3 | 1 |  |  | 1 | 20 | 2014-05-05 12:00 | 2014-05-25 12:00 | Construct | Sets->Architectural->Interior->Doors->Arch-Int-Doors-L4 |  |  | 300-2-8-4 | 300-2-8-4 |  | Scale | 0% | 0 | 273700 | 28000 | 0 | 0
1 | Arch-Int-Doors-L5 | 3 | 1 |  |  | 1 | 18 | 2014-05-25 12:00 | 2014-06-12 12:00 | Construct | Sets->Architectural->Interior->Doors->Arch-Int-Doors-L5 |  |  | 300-2-8-5 | 300-2-8-5 |  | Scale | 0% | 0 | 243100 | 25200 | 0 | 0
1 | Arch-Int-Doors-L6 | 3 | 1 |  |  | 1 | 2 | 2014-06-12 12:00 | 2014-06-14 12:00 | Construct | Sets->Architectural->Interior->Doors->Arch-Int-Doors-L6 |  |  | 300-2-8-6 | 300-2-8-6 |  | Scale | 0% | 0 | 12000 | 8000 | 0 | 0
1 | Ceilings | 2 | 1 |  |  | 1 | [7 empty] | 300-2-9 | 300-2-9 |  | Scale | 0% | 0
1 | Arch-Int-Ceiling-L1 | 3 | 1 |  |  | 1 | 15 | 2014-04-16 12:00 | 2014-05-01 12:00 | Construct | Sets->Architectural->Interior->Ceilings->Arch-Int-Ceiling-L1 |  |  | 300-2-9-1 | 300-2-9-1 |  | Scale | 0% | 0 | 988000 | 411200 | 0 | 33000
1 | Arch-Int-Ceiling-L2 | 3 | 1 |  |  | 1 | 15 | 2014-05-01 12:00 | 2014-05-16 12:00 | Construct | Sets->Architectural->Interior->Ceilings->Arch-Int-Ceiling-L2 |  |  | 300-2-9-2 | 300-2-9-2 |  | Scale | 0% | 0 | 888000 | 200000 | 0 | 33000
1 | Arch-Int-Ceiling-L3 | 3 | 1 |  |  | 1 | 15 | 2014-05-16 12:00 | 2014-05-31 12:00 | Construct | Sets->Architectural->Interior->Ceilings->Arch-Int-Ceiling-L3 |  |  | 300-2-9-3 | 300-2-9-3 |  | Scale | 0% | 0 | 788000 | 190000 | 0 | 33000
1 | Arch-Int-Ceiling-L4 | 3 | 1 |  |  | 1 | 15 | 2014-05-31 12:00 | 2014-06-15 12:00 | Construct | Sets->Architectural->Interior->Ceilings->Arch-Int-Ceiling-L4 |  |  | 300-2-9-4 | 300-2-9-4 |  | Scale | 0% | 0 | 488000 | 130000 | 0 | 33000
1 | Arch-Int-Ceiling-L5 | 3 | 1 |  |  | 1 | 15 | 2014-06-15 12:00 | 2014-06-30 12:00 | Construct | Sets->Architectural->Interior->Ceilings->Arch-Int-Ceiling-L5 |  |  | 300-2-9-5 | 300-2-9-5 |  | Scale | 0% | 0 | 488000 | 130000 | 0 | 33000
1 | Plumbing Fixtures | 2 | 1 |  |  | 1 | [7 empty] | 300-2-10 | 300-2-10 |  | Scale | 0% | 0
1 | Arch-Int-GrabBar+Stalls-All Levels | 3 | 1 |  |  | 1 | 5 | 2014-06-16 12:00 | 2014-06-21 12:00 | Construct | Sets->Architectural->Interior->Plumbing->Arch-Int-GrabBar+Stalls-All Levels |  |  | 300-2-10-1 | 300-2-10-1 |  | Scale | 0% | 0 | 989000 | 0 | 0 | 0
1 | Furniture | 2 | 1 |  |  | 1 | [7 empty] | 300-2-11 | 300-2-11 |  | Scale | 0% | 0
1 | Arch-Int-Dining_Tables+Chairs | 3 | 1 |  |  | 1 | 1 | 2014-07-13 12:00 | 2014-07-14 12:00 | Construct | Sets->Architectural->Interior->Furniture->Arch-Int-Dining_Tables+Chairs |  |  | 300-2-11-1 | 300-2-11-1 |  | Scale | 0% | 0 | 850000 | 0 | 0 | 55000
1 | Arch-Int-LectureRm_Tables+Chairs | 3 | 1 |  |  | 1 | 1 | 2014-07-13 12:00 | 2014-07-14 12:00 | Construct | Sets->Architectural->Interior->Furniture->Arch-Int-LectureRm_Tables+Chairs |  |  | 300-2-11-2 | 300-2-11-2 |  | Scale | 0% | 0 | 350000 | 0 | 0 | 25000
1 | Arch-Solar Panels | 1 | 1 |  |  | 1 | 30 | 2013-09-24 12:00 | 2013-10-24 12:00 | Construct | Sets->Architectural->Arch-Solar Panels |  |  | 300-2-12 | 300-2-12 |  | Scale | 0% | 0 | 1270000 | 0 | 0 | 55000
1 | Arch-Wind Turbines | 1 | 1 |  |  | 1 | 30 | 2013-10-24 12:00 | 2013-11-23 12:00 | Construct | Sets->Architectural->Arch-Wind Turbines |  |  | 300-2-13 | 300-2-13 |  | Scale | 0% | 0 | 2000000 | 0 | 0 | 25000
1 | Life_Flight_Helicopter | 1 | 1 |  |  | 1 | 0.5 | 2014-07-23 12:00 | 2014-07-24 | Construct | Sets->Architectural->Life_Flight_Helicopter |  |  | 300-2-14 | 300-2-14 |  | Scale | 0% | 0 | 2250000 | 0 | 0 | 0
1 | Semi Trucks | 1 | 1 |  |  | 1 | 1 | 2014-07-23 12:00 | 2014-07-24 12:00 | Construct | Sets->Architectural->Semi Trucks |  |  | 300-2-15 | 300-2-15 |  | Scale | 0% | 0 | 500000 | 0 | 0 | 0
1 | Electrical | 0 | 1 |  |  | 1 | [7 empty] | 400 | 400 |  | Scale | 0% | 0
1 | Elect-Equip,Tray,Conduit | 1 | 1 |  |  | 1 | 4 | 2013-09-21 12:00 | 2013-09-25 12:00 | Construct | Sets->Electrical->Elect-Equip,Tray,Conduit |  |  | 400-1 | 400-1 |  | Scale | 0% | 0 | 1550000 | 90000 | 0 | 0
1 | Elect-Motors | 1 | 1 |  |  | 1 | 4 | 2013-09-20 12:00 | 2013-09-24 12:00 | Construct | Sets->Electrical->Elect-Motors |  |  | 400-2 | 400-2 |  | Scale | 0% | 0 | 1170000 | 100000 | 0 | 0
1 | Elect-Receptacles-All | 1 | 1 |  |  | 1 | 8 | 2014-06-13 12:00 | 2014-06-21 12:00 | Construct | Sets->Electrical->Elect-Receptacles |  |  | 400-3 | 400-3 |  | Scale | 0% | 0 | 430000 | 190000 | 0 | 0
1 | Elect-LightFixtures-All | 1 | 1 |  |  | 1 | 14 | 2014-07-02 12:00 | 2014-07-16 12:00 | Construct | Sets->Electrical->Elect-LightFixtures |  |  | 400-4 | 400-4 |  | Scale | 0% | 0 | 1750000 | 195000 | 0 | 0
1 | Elect-NurseCallDevices | 1 | 1 |  |  | 1 | 10 | 2014-07-02 12:00 | 2014-07-12 12:00 | Construct | Sets->Electrical->Elect-NurseCallDevices |  |  | 400-5 | 400-5 |  | Scale | 0% | 0 | 500000 | 170000 | 0 | 0
1 | Elect-DataOutlet | 1 | 1 |  |  | 1 | 10 | 2014-07-02 12:00 | 2014-07-12 12:00 | Construct | Sets->Electrical->Elect-DataOutlet |  |  | 400-6 | 400-6 |  | Scale | 0% | 0 | 450000 | 60000 | 0 | 0
1 | HVAC | 0 | 1 |  |  | 1 | [7 empty] | 500 | 500 |  | Scale | 0% | 0
1 | HVAC-Rooftop-Equip | 1 | 1 |  |  | 1 | 3 | 2013-09-21 12:00 | 2013-09-24 12:00 | Construct | Sets->HVAC->HVAC-Rooftop-Equip |  |  | 500-1 | 500-1 |  | Scale | 0% | 0 | 2500000 | 700000 | 0 | 0
1 | HVAC-Rooftop-Ducts+Pipes | 1 | 1 |  |  | 1 | 5 | 2013-09-24 12:00 | 2013-09-29 12:00 | Construct | Sets->HVAC->HVAC-Rooftop-Ducts+Pipes |  |  | 500-2 | 500-2 |  | Scale | 0% | 0 | 1850000 | 700000 | 0 | 0
1 | HVAC-Ducts-L5 | 1 | 1 |  |  | 1 | 12 | 2013-09-29 12:00 | 2013-10-11 12:00 | Construct | Sets->HVAC->HVAC-Ducts-L5 |  |  | 500-3 | 500-3 |  | Scale | 0% | 0 | 1700000 | 550000 | 0 | 0
1 | HVAC-Ducts-L4 | 1 | 1 |  |  | 1 | 12 | 2013-10-11 12:00 | 2013-10-23 12:00 | Construct | Sets->HVAC->HVAC-Ducts-L4 |  |  | 500-4 | 500-4 |  | Scale | 0% | 0 | 1700000 | 550000 | 0 | 0
1 | HVAC-Ducts-L3 | 1 | 1 |  |  | 1 | 12 | 2013-10-23 12:00 | 2013-11-04 12:00 | Construct | Sets->HVAC->HVAC-Ducts-L3 |  |  | 500-5 | 500-5 |  | Scale | 0% | 0 | 1700000 | 550000 | 0 | 0
1 | HVAC-Ducts-L2 | 1 | 1 |  |  | 1 | 18 | 2013-11-04 12:00 | 2013-11-22 12:00 | Construct | Sets->HVAC->HVAC-Ducts-L2 |  |  | 500-6 | 500-6 |  | Scale | 0% | 0 | 1700000 | 550000 | 0 | 0
1 | HVAC-Ducts-L1 | 1 | 1 |  |  | 1 | 18 | 2013-11-22 12:00 | 2013-12-10 12:00 | Construct | Sets->HVAC->HVAC-Ducts-L1 |  |  | 500-7 | 500-7 |  | Scale | 0% | 0 | 1710000 | 550000 | 0 | 0
1 | HVAC-Diffusers | 1 | 1 |  |  | 1 | 10 | 2014-07-04 12:00 | 2014-07-14 12:00 | Construct | Sets->HVAC->HVAC-Diffusers |  |  | 500-8 | 500-8 |  | Scale | 0% | 0 | 1020000 | 250000 | 0 | 0
1 | Mech-Pipes_MedGasOutlet-L1-L5 | 1 | 1 |  |  | 1 | 10 | 2014-06-16 12:00 | 2014-06-26 12:00 | Construct | Sets->HVAC->HVAC-Pipes_MedGasOutlet-L1-L5 |  |  | 500-9 | 500-9 |  | Scale | 0% | 0 | 1321400 | 500000 | 0 | 0
1 | Plumbing | 0 | 1 |  |  | 1 | [7 empty] | 600 | 600 |  | Scale | 0% | 0
1 | Piping and Fittings | 1 | 1 |  |  | 1 | [7 empty] | 600-1 | 600-1 |  | Scale | 0% | 0
1 | Plumb-Pipe+Fittings-L1 | 2 | 1 |  |  | 1 | 8 | 2013-09-21 12:00 | 2013-09-29 12:00 | Construct | Sets->Plumbing->Piping and Fittings->Plumb-Pipe+Fittings-L1 |  |  | 600-1-1 | 600-1-1 |  | Scale | 0% | 0 | 1282500 | 0 | 0 | 35200
1 | Plumb-Pipe+Fittings-L2 | 2 | 1 |  |  | 1 | 10 | 2013-09-29 12:00 | 2013-10-09 12:00 | Construct | Sets->Plumbing->Piping and Fittings->Plumb-Pipe+Fittings-L2 |  |  | 600-1-2 | 600-1-2 |  | Scale | 0% | 0 | 1282500 | 0 | 0 | 44000
1 | Plumb-Pipe+Fittings-L3 | 2 | 1 |  |  | 1 | 12 | 2013-10-09 12:00 | 2013-10-21 12:00 | Construct | Sets->Plumbing->Piping and Fittings->Plumb-Pipe+Fittings-L3 |  |  | 600-1-3 | 600-1-3 |  | Scale | 0% | 0 | 1282500 | 0 | 0 | 52800
1 | Plumb-Pipe+Fittings-L4 | 2 | 1 |  |  | 1 | 12 | 2013-10-21 12:00 | 2013-11-02 12:00 | Construct | Sets->Plumbing->Piping and Fittings->Plumb-Pipe+Fittings-L4 |  |  | 600-1-4 | 600-1-4 |  | Scale | 0% | 0 | 1282500 | 0 | 0 | 52800
1 | Plumb-Pipe+Fittings-L5 | 2 | 1 |  |  | 1 | 10 | 2013-11-02 12:00 | 2013-11-12 12:00 | Construct | Sets->Plumbing->Piping and Fittings->Plumb-Pipe+Fittings-L5 |  |  | 600-1-5 | 600-1-5 |  | Scale | 0% | 0 | 1282500 | 0 | 0 | 44000
1 | Fixtures | 1 | 1 |  |  | 1 | [7 empty] | 600-2 | 600-2 |  | Scale | 0% | 0
1 | Plumb-Fixtures-L1 | 2 | 1 |  |  | 1 | 3 | 2014-06-13 12:00 | 2014-06-16 12:00 | Construct | Sets->Plumbing->Fixtures->Plumb-Fixtures-L1 |  |  | 600-2-1 | 600-2-1 |  | Scale | 0% | 0 | 1532000 | 178000 | 0 | 6300
1 | Plumb-Fixtures-L2 | 2 | 1 |  |  | 1 | 3 | 2014-06-16 12:00 | 2014-06-19 12:00 | Construct | Sets->Plumbing->Fixtures->Plumb-Fixtures-L2 |  |  | 600-2-2 | 600-2-2 |  | Scale | 0% | 0 | 1532000 | 178000 | 0 | 6300
1 | Plumb-Fixtures-L3 | 2 | 1 |  |  | 1 | 5 | 2014-06-19 12:00 | 2014-06-24 12:00 | Construct | Sets->Plumbing->Fixtures->Plumb-Fixtures-L3 |  |  | 600-2-3 | 600-2-3 |  | Scale | 0% | 0 | 1532000 | 178000 | 0 | 10500
1 | Plumb-Fixtures-L4 | 2 | 1 |  |  | 1 | 5 | 2014-06-24 12:00 | 2014-06-29 12:00 | Construct | Sets->Plumbing->Fixtures->Plumb-Fixtures-L4 |  |  | 600-2-4 | 600-2-4 |  | Scale | 0% | 0 | 1532000 | 178000 | 0 | 10500
1 | Plumb-Fixtures-L5 | 2 | 1 |  |  | 1 | 4 | 2014-06-29 12:00 | 2014-07-03 12:00 | Construct | Sets->Plumbing->Fixtures->Plumb-Fixtures-L5 |  |  | 600-2-5 | 600-2-5 |  | Scale | 0% | 0 | 1532000 | 178000 | 0 | 8400
1 | Fire Alarm and Sprinkler | 0 | 1 |  |  | 1 | [7 empty] | 700 | 700 |  | Scale | 0% | 0
1 | Sprinkler | 1 | 1 |  |  | 1 | [7 empty] | 700-1 | 700-1 |  | Scale | 0% | 0
1 | Sprinkler-L1 | 2 | 1 |  |  | 1 | 5 | 2013-10-02 12:00 | 2013-10-07 12:00 | Construct | Sets->Sprinkler->Sprinkler-L1 |  |  | 700-1-1 | 700-1-1 |  | Scale | 0% | 0 | 1705000 | 170000 | 0 | 16500
1 | Sprinkler-L2 | 2 | 1 |  |  | 1 | 5 | 2013-10-07 12:00 | 2013-10-12 12:00 | Construct | Sets->Sprinkler->Sprinkler-L2 |  |  | 700-1-2 | 700-1-2 |  | Scale | 0% | 0 | 1505000 | 150000 | 0 | 16500
1 | Sprinkler-L3 | 2 | 1 |  |  | 1 | 5 | 2013-10-12 12:00 | 2013-10-17 12:00 | Construct | Sets->Sprinkler->Sprinkler-L3 |  |  | 700-1-3 | 700-1-3 |  | Scale | 0% | 0 | 1505000 | 150000 | 0 | 16500
1 | Sprinkler-L4 | 2 | 1 |  |  | 1 | 5 | 2013-10-17 12:00 | 2013-10-22 12:00 | Construct | Sets->Sprinkler->Sprinkler-L4 |  |  | 700-1-4 | 700-1-4 |  | Scale | 0% | 0 | 1505000 | 150000 | 0 | 16500
1 | Sprinkler-L5 | 2 | 1 |  |  | 1 | 5 | 2013-10-22 12:00 | 2013-10-27 12:00 | Construct | Sets->Sprinkler->Sprinkler-L5 |  |  | 700-1-5 | 700-1-5 |  | Scale | 0% | 0 | 1505000 | 150000 | 0 | 16500
1 | Fire Alarm | 1 | 1 |  |  | 1 | [7 empty] | 700-2 | 700-2 |  | Scale | 0% | 0
1 | FireAlarm-Control_Panels | 2 | 1 |  |  | 1 | 3 | 2013-09-29 12:00 | 2013-10-02 12:00 | Construct | Sets->Fire Alarm->FireAlarm-Control_Panels |  |  | 700-2-1 | 700-2-1 |  | Scale | 0% | 0 | 1798500 | 400000 | 0 | 6300
1 | FireAlarm-Horn Strobes | 2 | 1 |  |  | 1 | 4 | 2014-07-01 12:00 | 2014-07-05 12:00 | Construct | Sets->Fire Alarm->FireAlarm-Horn Strobes |  |  | 700-2-2 | 700-2-2 |  | Scale | 0% | 0 | 1689000 | 350000 | 0 | 8400
1 | FireAlarm-Smoke Detectors | 2 | 1 |  |  | 1 | 4 | 2014-07-05 12:00 | 2014-07-09 12:00 | Construct | Sets->Fire Alarm->FireAlarm-Smoke Detectors |  |  | 700-2-3 | 700-2-3 |  | Scale | 0% | 0 | 1624000 | 30000 | 0 | 8400
1 | FireAlarm-Pull Stations | 2 | 1 |  |  | 1 | 4 | 2014-07-09 12:00 | 2014-07-13 12:00 | Construct | Sets->Fire Alarm->FireAlarm-Pull Stations |  |  | 700-2-4 | 700-2-4 |  | Scale | 0% | 0 | 1838000 | 400000 | 0 | 8400
Formulas:
Planned Start = [Planned Start, row above]
Planned Start = [Planned End, row above]
Planned End = [Planned Start]+[Duration]
Planned End = [Planned Start, row below]-1
Actual Start = [Planned Start]-5
Actual Start = [Planned Start]-5.92
Actual End = [Planned End]+0.375
Actual End = [Actual Start]+0.04